## Issue Log
Task Titans Issue Log Created by: Will Dzialak (Scrum Master)
ID | Brief Name | Description | Severity | Owner | Date Added | Status | Close Date | Notes on Closure
Unique identifier | Brief 3-5 word description of the issue | Description of the issue | Severity of this issue: 1-High, 2-Medium, 3-Low | Person who is responsible for evaluating and resolving this issue | Date this issue was added to this list | Status of item: 1-Open, 2-In Progress, 3-Closed | Date this issue was resolved | Notes or results on the resolution of this issue, such as final decision document location, results of implementing requested fix, etc
1 | Underestimated Budget | The budget was initially estimated during the early phases of the project, and eventually it was realized that the budget was too low | 1 | Project Manager | 2024-03-27 | 3 | 2024-04-03 | Met with key stakeholders (including the client) and the project was approved a higher budget to be able to afford the costs for all project stages
2 | Unclear Responsibilities | Several people working on the project were confused about their responsibilities for the testing portion of the project | 2 | Scrum Master and/or Project Manager | 2024-04-03 | 3 | 2024-04-16 | A RACI chart was created to eliminate confusion
3 | Lack of Collaboration | The ability to work effectively with the user group during testing was unclear because of personality differences | 2 | Scrum Master, QA & DevOps Lead, and/or Project Manager | 2024-04-03 | 3 | 2024-04-16 | Multiple solutions were compared to see which would be the best for the project. These included mediated feedback sessions and training on effective communication
4 | Poor Communication and Organization | The team was having difficulty deciding how to communicate various project reports and documents and where to store all of the information being generated | 1 | Project Manager | 2024-03-06 | 3 | 2024-03-20 | A communications management plan was created to enhance collaboration, ensure transparency, and drive project success through informed decision-making and stakeholder engagement
5 | Unknown Risks | The team was not being proactive in managing risks and was doing poorly at documenting them. | 1 | All team members | 2024-03-20 | 3 | 2024-03-27 | A risk register was created to define risks. Proper responses for these risks were brainstormed and risk owners identified