## Project Estimate
NutriScope Project Cost Estimate
Prepared by: William Dzialak (Scrum Master) | Date: 4/16/2024
WBS Items | # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total | Assumptions
1. NutriScope Health Tracker | [5 empty] | [1] No additional HW needs to be purchased
1.1 Initiation |  |  |  | 3465 | 0.6261% | [2] Stakeholders met and approved a larger budget after reviewing cost estimates
1.1.1 Project Manager Support | 8.5 | 120 | 1020 |  |  | [3] Eliminated customer support team expanision to save costs
1.1.2 Project Team Members Support | 32.6 | 75 | 2445
1.2 Planning |  |  |  | 51248.5 | 9.26%
1.2.1 Project Manager Support | 135.3 | 120 | 16236
1.2.2 Project Team Members Support | 333.5 | 75 | 25012.5
1.2.3 Interview, Survey, and Workshop Materials | 1 | 10000 | 10000
1.3 Execution |  |  |  | 315758 | 57.05%
1.3.1 Licensed software
1.3.1.1 Enhanced Encryption Protocols | 1 | 5000 | 5000
1.3.1.2 Intrusion Detection System (IDS) | 1 | 10000 | 10000
1.3.1.2.1 Monthly Maintenance | 12 | 500 | 6000
1.3.1.3 Customer Relationship Management (CRM) System | 1 | 10000 | 10000
1.3.1.3.1 Monthly Subscription Fee | 12 | 1000 | 12000
1.3.1.4 Cloud Services Scaling | 12 | 3000 | 36000
1.3.2 Software development* |  |  | 236758
1.4 Monitoring/Controlling |  |  |  | 41567 | 7.51%
1.4.1 Training and Support
1.4.1.1 Cybersecurity Training (once per year) | 1 | 2000 | 2000
1.4.2 Project Manager Support | 66.6 | 120 | 7992
1.4.3 Project Team Members Support | 421 | 75 | 31575
1.4.4 Testing (10% of total hardware and software costs) |  |  | 31575.8 | 31575.8 | 5.705%
1.5 Closure |  |  |  | 37653 | 6.803%
1.5.1 Project Manager Support | 30.4 | 120 | 3648
1.5.2 Project Team Members Support | 53.4 | 75 | 4005
1.5.3 Security Audits
1.5.3.1 Initial Security Audit | 1 | 10000 | 10000
1.5.3.2 Biannual Security Audit | 2 | 10000 | 20000
Reserves (15% of total estimate) |  |  | 72190.095 | 72190.095 | 13.04%
Total project cost estimate |  |  |  | 553457.395
* See software development estimate tab
| Budget = $600,000 | Over-budget [ ]
Under-budget [X]

## SW Dev Estimate
* Software development
Project team member estimate (entire team during execution besides PM) | 312.89 | 75 | 23466.75
Total labor estimate |  |  | 23466.75
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 6 | 4 | 24
External interfaces | 3 | 7 | 21
External outputs | 4 | 5 | 20
External inqueries | 2 | 4 | 8
Logical internal tables/files | 6 | 10 | 60
Total function points |  |  | 133 | Programming Language: Javascript (value = 47)
Javascript languange equivalency value |  |  | 47
Source lines of code (SLOC) estimate |  |  | 6251
Productivity * (KSLOC)^Penalty (person months)** | 19.7298
Total labor hours (160 hours/month) | 3156.775
Cost/labor hour ($75/hour) | 75
Total software development estimate | 236758.1271
** (Penalty = 1.11 for embedded development)
** (Productivity = 2.58 for embedded development)
(Conversion factor used is the average for each category according to the industry standard)
References
https://eljabiri1.tripod.com/sitebuildercontent/sitebuilderfiles/Cost-Estimation-Tutorial.pdf
https://www.geeksforgeeks.org/software-engineering-functional-point-fp-analysis/
https://www.qsm.com/resources/function-point-languages-table
Definitions
1. External Inputs: these are end-user actions such as putting in a login or executing a mouse click.
2. External Outputs: the system provides the end-user output or interface such as a GUI display or items in a report.
3. Logical Internal Files: these files are the master or transaction files that the system interacts with during its session.
4. External Interface Files: unlike logical internal files, where the application uses solely for its purpose, these files are or databases are shared with other applications or systems.
5. External Inquiries: this function is initiated by the end-user. For example, the end-user wishes to submit a query to a database or requests on-line help. In any case the developer provides a means for the end-user to "search" for answers.