## Sheet1
Risk Register for NutriScope (Health Metrics Project)
Prepared by: Jayesh Pamnani |  |  |  |  | Date: Mar 31, 2024
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Risk Score | Status
5 | 1 | Data Privacy Breaches | If data privacy is breached, then it could result in legal penalties and loss of user trust, severely impacting the project's success and financial stability. | Security | Inadequate security measures and protocols. | Data breach incidents, unauthorized access detected. | Develop and implement a comprehensive cybersecurity strategy that encompasses state-of-the-art encryption technologies, deployment of a sophisticated intrusion detection system, periodic security audits by an external specialized firm, and a rigorous staff training program to foster a culture of security awareness. | Security Officer | 9 | 9 | 81 | Identified
1 | 2 | Key Team Members Leaving | If key team members leave the company, then project progress will be disrupted, leading to delays. | Human Resources | Competitive job market and internal dissatisfaction. | Resignations, recruitment offers from other companies. | Implement retention strategies, backup plan for key positions. | HR Manager | 8 | 8 | 64 | Identified
7 | 3 | Regulatory Compliance Failures | If the project fails to comply with regulatory changes or requirements, then it could face legal penalties, project delays, and increased costs for compliance measures. | Legal | Lack of awareness or focus on legal and regulatory requirements. | Legal notices, changes in data protection laws. | Regular legal reviews, compliance audits, and training. | Compliance Officer | 7 | 8 | 56 | Identified
2 | 4 | Uncooperative Users | If users are uncooperative during the feedback and testing phases, then the quality and user-centric design of the application could be compromised. | Stakeholder | Lack of engagement strategy or incentives for users. | Negative feedback, refusal to use the app for feedback. | Increase user engagement through incentives and communication. | Project Manager | 7 | 6 | 42 | Identified
3 | 5 | Poor Status Reporting | If team members fail to provide accurate and timely status updates, then project management could become inefficient, leading to overlooked tasks and delays. | Communication | Inadequate project management tools or processes. | Missed deadlines, inconsistent reports. | Improve project management practices, regular status meetings. | Project Manager | 6 | 7 | 42 | Identified
4 | 6 | Integration with Wearables | If seamless integration with various wearable devices fails, then the app's core functionality and market competitiveness could be significantly affected. | Technical | Technical limitations and compatibility issues. | Integration failures, data mismatch. | Research and develop flexible integration solutions. | Technical Lead | 5 | 7 | 35 | Identified
6 | 7 | Over-reliance on Internet Connectivity | If the app relies too heavily on internet connectivity, then users with unstable connections might experience reduced functionality, affecting user satisfaction and adoption rates. | Technical | Assumption of universal high-speed internet access. | User complaints about accessibility, performance issues. | Develop offline functionality, optimize performance. | Technical Lead | 4 | 5 | 20 | Identified
8 | 8 | High User Adoption Rate | If the app experiences a higher-than-expected user adoption rate, then the existing infrastructure might be overwhelmed, leading to performance issues and increased operational costs. | Opportunity | Underestimation of market demand and scalability requirements. | Server overload, high customer service requests. | Establish a scalable infrastructure to handle increased user loads effectively, including server elasticity, database optimization, and reinforced customer support. A systematic CRM system will be introduced to manage growing user interactions efficiently. | Operations Manager | 3 | 4 | 12 | Identified
9 | 9 | Successful Marketing Campaign | If the marketing campaign is more successful than anticipated, then user engagement and brand awareness could significantly increase. | Opportunity | Effective marketing strategy and execution. | Higher than expected campaign reach and user engagement. | Prepare marketing and operational strategies to capitalize on increased user base. | Marketing Manager | 6 | 2 | 12 | Identified